## Iteration 1
Task | Type | Category | Start Date | End Date | Hours needed | Assigned to | Completed |  | Hours | Non-Programming | Programming
Project Preparation ▼
Gathering Requirements | Non-Programming | Iteration Preparation | 2016-04-27 | 2016-05-01 | 2 | ALL |  | Total | 294 | 145 | 149
Researching on external libraries | Non-Programming | Iteration Preparation | 2016-04-27 | 2016-04-27 | 2 | ALL
Researching on UI Templates | Non-Programming | Iteration Preparation | 2016-05-01 | 2016-05-01 | 2 | ALL |  | *Huxley* | 48 | 5 | 43
UI Prototyping | Non-Programming | Iteration Preparation | 2016-05-01 | 2016-05-01 | 2 | ALL |  | *SiHao* | 48 | 5 | 43
[8 empty] | *Marcus* | 50 | 2 | 48
End Of Preparation | [7 empty] | *Darryl* | 68 | 68 | 0
Start Of Iteration 1 (2/5/16 - 15/5/16) | [7 empty] | *Thao* | 50 | 2 | 48
Iteration Preparation ▼ | [7 empty] | *ALL* | 10 | 10 | 0
Set up Bitbucket | Non-Programming | Iteration Preparation | 2016-05-05 | 2016-05-05 | 2 | ALL
Planning of Schedule | Non-Programming | Iteration Preparation | 2016-05-05 | 2016-05-05 | 2 | Darryl
Design ▼ | [7 empty] | Our Total | 274 | 92 | 182
Create Use Case Diagram | Non-Programming | Design | 2016-04-27 | 2016-04-27 | 2 | Huxley, SiHao |  | Overlapping Hours | -20 | -53 | 33
Create ER Diagram | Non-Programming | Design | 2016-05-05 | 2016-05-05 | 2 | Marcus, Thao
Create Logical Design Diagram | Non-Programming | Design | 2016-05-06 | 2016-05-06 | 2 | Darryl
Create Contact Management Sequence Diagram - Create Contact - View Contact | Non-Programming | Design | 2016-05-06 | 2016-05-06 | 2 | Darryl
Coding ▼
UI Mockup
Develop GUI for Home + Login Develop GUI for HomeSP2(Simplified) | Programming | Coding | 2016-05-06 | 2016-05-06 | 2 | Marcus, Thao
Develop GUI for Create Contact Develop GUI for View Contact | Programming | Coding | 2016-05-06 | 2016-05-06 | 2 | Marcus, Thao
**Refer to UI Mockup in Shared folder
Database
Create and Setup Database Tables: - Contacts - User - Phone, Email, Address - Membership - Office_Held - Donation - Team - Team_Join - Training - Appreciation - Proxy - Language, Skill | Programming | Coding | 2016-05-07 | 2016-05-08 | 3 | Huxley, SiHao
Create and Setup Database Tables: - Event - Event_Affiliation - Event_Participations - Notices - Addressees | Programming | Coding | 2016-05-07 | 2016-05-08
End of Iteration Tasks ▼
Collection Task metric | Non-Programming | End of Iteration Task | 2016-05-12 | 2016-05-14 | 1 | Darryl
Update Documents - Class Diagram/Sequence Diagram/Agenda | Non-Programming | End of Iteration Task | 2016-05-12 | 2016-05-15 | 2 | Darryl
End Of Iteration 1 (2/5/16 - 15/5/16)
Start Of Iteration 2 (16/5/16 - 29/5/16)
Iteration Preparation ▼
Preparation/Agenda for Client Meeting (18 May) - Functionalities update - Schedule - Milestone - Buffer Time - Critical Path | Non-Programming | Iteration Preparation | 2016-05-16 | 2016-05-17 | 3 | Darryl
Follow-up after Client Meeting - Update Requirement Change - Mitigation Plan - Update Schedule | Non-Programming | Iteration Preparation | 2016-05-18 | 2016-05-19 | 3 | Darryl
Design ▼
Create Events Management Sequence Diagram - Create Event - View Event - Edit Event | Non-Programming | Design | 2016-05-18 | 2016-05-19 | 3 | Darryl
Coding ▼
UI Mockup - Event/Notices
Develop GUI for Create Event Develop GUI for View Event | Programming | Coding | 2016-05-06 | 2016-05-06 | 2 | Marcus, Thao
Develop GUI for Create Notices Develop GUI for View Notices | Programming | Coding | 2016-05-11 | 2016-05-11 | 2 | Marcus, Thao
Entity and DAO
Develop Entity Classes for all tables in the database | Programming | Coding | 2016-05-09 | 2016-05-11 | 2 | Huxley, SiHao
Develop DAO Classes for all tables in the database | Programming | Coding | 2016-05-12 | 2016-05-14 | 3 | Huxley, SiHao
Develop DAO class - Write methods and sql query for "retrieving event based on name"/"retrieving event based on date" - Write methods and sql query for "retrieving contacts based on name"/"retrieving event based on date" - Write methods and sql query for "retrieving notices based on name"/"retrieving event based on date" | Programming | Coding | 2016-05-16 | 2016-05-18 | 6 | Huxley, SiHao
Integration ▼
Integrating & testing with earlier functionalities | Programming | Integration | 2016-05-27 | 2016-05-27 | 1 | Marcus, Thao
Deployment ▼
Deploy application to XXX & resolving deployment issue | Non-Programming | Deployment | 2016-05-27 | 2016-05-27 | 1 | Huxley, SiHao
Regression Testing & Debugging ▼
Testing of application and documenting bugs | Programming | Regression Testing & Debugging | 2016-05-28 | 2016-05-28 | 1 | Huxley, SiHao
Debugging | Programming | Regression Testing & Debugging | 2016-05-28 | 2016-05-28 | 2 | Huxley, SiHao
End of Iteration Tasks ▼
Collection Task metric | Non-Programming | End of Iteration Task | 2016-05-28 | 2016-05-28 | 2 | Darryl
Update Documents - Class Diagram/Sequence Diagram/Agenda | Non-Programming | End of Iteration Task | 2016-05-28 | 2016-05-28 | 2 | Darryl
Code sharing | Non-Programming | End of Iteration Task | 2016-05-28 | 2016-05-28 | 1 | Darryl
End Of Iteration 2 (16/5/16 - 29/5/16)
Start Of Iteration 3 (30/5/16 - 12/6/16)
Iteration Preparation ▼
Preparation/Agenda for Client Meeting (1 June) - Functionalities update - Schedule - Milestone - Buffer Time - Critical Path | Non-Programming | Iteration Preparation | 2016-05-30 | 2016-05-30 | 3 | Darryl
Follow-up after Client Meeting - Update Requirement Change - Mitigation Plan - Update Schedule | Non-Programming | Iteration Preparation | 2016-06-02 | 2016-06-02 | 3 | Darryl
Design ▼
Complete/refine all technical documents - Use Case Diagrams - Sequence Diagrams - Class Diagram(s) - Logical Diagram | Non-Programming | Design | 2016-05-31 | 2016-05-31 | 3 | Darryl
Develop test cases (Generate Volunteer Report) | Non-Programming | Design | 2016-06-01 | 2016-06-01 | 1 | Darryl
Develop test cases (Generate Member Report) | Non-Programming | Design | 2016-06-01 | 2016-06-01 | 1 | Darryl
Develop test cases (Generate Donation Report) | Non-Programming | Design | 2016-06-02 | 2016-06-02 | 1 | Darryl
Develop test cases (Generate Events Report) | Non-Programming | Design | 2016-06-02 | 2016-06-02 | 1 | Darryl
Coding ▼
UI Mockup - Home/Events/Notices/Contacts
Integrate Retrieve Events function into Homepage | Programming | Coding | 2016-05-18 | 2016-05-20 | 3 | Marcus, Thao
Integrate Retrieve Notices function into Homepage | Programming | Coding | 2016-05-18 | 2016-05-20 | 3 | Marcus, Thao
Develop Homepage such that details of Event can be hidden | Programming | Coding | 2016-05-21 | 2016-05-21 | 3 | Marcus, Thao
Develop "Search Contact" Page | Programming | Coding | 2016-05-22 | 2016-05-23 | 2 | Marcus, Thao
Develop "Search Event" and "Search Notice" Page | Programming | Coding | 2016-05-24 | 2016-05-24 | 2 | Marcus, Thao
**Refer to UI Mockup in Shared folder
Input Validation Utility
Create field validation utility | Programming | Coding | 2016-05-19 | 2016-05-21 | 3 | Huxley, SiHao
Access Control Module
Develop Role Based Access Control (restrict view/edit settings of different users) -- based on Permission Level provided - Team Manager - Admin | Programming | Coding | 2016-05-22 | 2016-05-23 | 5 | Huxley, SiHao
Develop Role Based Access Control (restrict view/edit settings of different users) -- based on Permission Level provided - Novice - Associate - Event Leader | Programming | Coding | 2016-05-30 | 2016-05-31 | 4 | Huxley, SiHao
Integration ▼
Integrating & testing with earlier functionalities | Programming | Integration | 2016-06-06 | 2016-06-06 | 3 | Huxley, SiHao
Deployment ▼
Deploy application to XXX | Non-Programming | Deployment | 2016-06-06 | 2016-06-06 | 2 | Huxley, SiHao
Regression Testing & Debugging ▼
Testing of application and documenting bugs | Programming | Regression Testing & Debugging | 2016-06-07 | 2016-06-07 | 2 | Marcus, Thao
Debugging | Programming | Regression Testing & Debugging | 2016-06-07 | 2016-06-07 | 2 | Marcus, Thao
End of Iteration Tasks ▼
Collection Schedule and PP metric | Non-Programming | End of Iteration Task | 2016-06-07 | 2016-06-07 | 2 | Darryl
Code sharing | Non-Programming | End of Iteration Task | 2016-06-07 | 2016-06-07 | 2 | Darryl
Prepare for Proposal Submission | Non-Programming | End of Iteration Task | 2016-06-07 | 2016-06-10 | 4 | Darryl
End Of Iteration 3 (30/5/16 - 12/6/16)
Start Of Iteration 4 (13/6/16 - 26/6/16)
Iteration Preparation ▼
Preparation/Agenda for Client Meeting (15 June) - Functionalities update - Schedule - Milestone - Buffer Time - Critical Path | Non-Programming | Iteration Preparation | 2016-06-13 | 2016-06-13 | 3 | Darryl
Follow-up after Client Meeting - Update Requirement Change - Mitigation Plan - Update Schedule | Non-Programming | Iteration Preparation | 2016-06-16 | 2016-06-16 | 3 | Darryl
Design ▼
Finish Up documentations | Non-Programming | Design | 2015-11-03 | 2015-11-03 | 2
Final Preparation for UAT test | Non-Programming | Design | 2015-11-02 | 2015-11-06 | 6
Develop test cases (Social Activeness Report) | Non-Programming | Design | 2015-10-26 | 2015-10-26 | 2
Coding ▼
UI Mockup - Home/Events/Notices/Contacts
Integrate Search Function into Contacts Page | Programming | Coding | 2016-05-25 | 2016-05-26 | 2 | Marcus, Thao
Integrate Search Function into Events and Notices Page | Programming | Coding | 2016-05-27 | 2016-05-27 | 2 | Marcus, Thao
Develop Report Main Page | Programming | Coding | 2016-05-30 | 2016-05-30 | 2 | Marcus, Thao
**Refer to UI Mockup in Shared folder
UI Mockup - Reports
Develop DAO class - Write methods and sql query for "retrieving volunteers based on team" - Write methods and sql query to "count number of volunteers within a certain period" - Write methods and sql query to "sort volunteers record in periodic order" - Write methods and sql query to "sort volunteers record in alphabatical order" | Programming | Coding | 2016-05-30 | 2016-05-31 | 4 | Huxley, SiHao
Develop DAO class - Write methods and sql query for "retrieving members based on team and date" - Write methods and sql query to "count total number of active members" - Write methods and sql query to "count number of members from a certain class" | Programming | Coding | 2016-06-03 | 2016-06-04 | 3 | Huxley, SiHao
Integration ▼
Integrating & testing with earlier functionalities | Programming | Integration | 2015-10-29 | 2015-10-30 | 2
Deployment ▼
Deploy application to OpenShift | Programming | Deployment | 2015-10-29 | 2015-10-30 | 2
Regression Testing & Debugging ▼
Testing of application and documenting bugs | Programming | Regression Testing & Debugging | 2015-10-29 | 2015-10-30 | 2
Debugging | Programming | Regression Testing & Debugging | 2015-10-29 | 2015-10-30 | 2
End of Iteration Tasks ▼
Collection Schedule and PP metric | Non-Programming | End of Iteration Task | 2015-10-30 | 2015-10-30 | 1
Code sharing | Non-Programming | End of Iteration Task | 2015-10-30 | 2015-10-30 | 1
End Of Iteration 4 (13/6/16 - 26/6/16)
Start Of Iteration 5 (27/6/16 - 10/7/16)
Iteration Preparation ▼
Preparation/Agenda for Client Meeting (29 June) - Functionalities update - Schedule - Milestone - Buffer Time - Critical Path | Non-Programming | Iteration Preparation | 2016-06-13 | 2016-06-13 | 3 | Darryl
Follow-up after Client Meeting - Update Requirement Change - Mitigation Plan - Update Schedule | Non-Programming | Iteration Preparation | 2016-06-16 | 2016-06-16 | 3 | Darryl
Design ▼
Finish Up documentations | Non-Programming | Design | 2015-11-03 | 2015-11-03 | 2
Final Preparation for UAT test | Non-Programming | Design | 2015-11-02 | 2015-11-06 | 6
Develop test cases (Social Activeness Report) | Non-Programming | Design | 2015-10-26 | 2015-10-26 | 2
Coding ▼
UI Mockup - Reports
Develop "Generate report of volunteers as of today" Page | Programming | Coding | 2016-05-31 | 2016-05-31 | 1 | Marcus, Thao
Develop "Generate report of members as of specified date" Page | Programming | Coding | 2016-05-31 | 2016-05-31 | 1 | Marcus, Thao
Develop "Generate report of donations" Page | Programming | Coding | 2016-06-01 | 2016-06-01 | 1 | Marcus, Thao
Develop "Generate report of events" Page | Programming | Coding | 2016-06-01 | 2016-06-01 | 1 | Marcus, Thao
**Refer to UI Mockup in Shared folder
Report Module
Develop DAO class - Write methods and sql query for "retrieving donations based on start date and end date" - Write methods and sql query to "sort donations in descending order" - Write methods and sql query to "sort donations in alphabatical order" | Programming | Coding | 2016-06-05 | 2016-06-06 | 2 | Huxley, SiHao
Develop DAO class - Write methods and sql query for "retrieving events based on start date and end date" - Write methods and sql query for "retrieving events based on team, start date and end date" - Write methods and sql query to "sort events record in periodic order" - Write methods and sql query to "sort events record in alphabatical order" | Programming | Coding | 2016-06-07 | 2016-06-08 | 2 | Huxley, SiHao
**Refer to UI Mockup in Shared folder
Integration ▼
Integrating & testing with earlier functionalities | Programming | Integration | 2015-10-29 | 2015-10-30 | 2
Deployment ▼
Deploy application to OpenShift | Programming | Deployment | 2015-10-29 | 2015-10-30 | 2
Regression Testing & Debugging ▼
Testing of application and documenting bugs | Programming | Regression Testing & Debugging | 2015-10-29 | 2015-10-30 | 2
Debugging | Programming | Regression Testing & Debugging | 2015-10-29 | 2015-10-30 | 2
End of Iteration Tasks ▼
Collection Schedule and PP metric | Non-Programming | End of Iteration Task | 2015-10-30 | 2015-10-30 | 1
Code sharing | Non-Programming | End of Iteration Task | 2015-10-30 | 2015-10-30 | 1
End Of Iteration 5 (27/6/16 - 10/7/16)
Start Of Iteration 6 (11/7/16 - 24/7/16)
Iteration Preparation ▼
Preparation/Agenda for Client Meeting (15 June) - Functionalities update - Schedule - Milestone - Buffer Time - Critical Path | Non-Programming | Iteration Preparation | 2016-06-13 | 2016-06-13 | 3 | Darryl
Follow-up after Client Meeting - Update Requirement Change - Mitigation Plan - Update Schedule | Non-Programming | Iteration Preparation | 2016-06-16 | 2016-06-16 | 3 | Darryl
Design ▼
Finish Up documentations | Non-Programming | Design | 2015-11-03 | 2015-11-03 | 2
Final Preparation for UAT test | Non-Programming | Design | 2015-11-02 | 2015-11-06 | 6
Develop test cases (Social Activeness Report) | Non-Programming | Design | 2015-10-26 | 2015-10-26 | 2
Coding ▼
UI Mockup
Develop User Management Page | Programming | Coding | 2015-10-26 | 2015-10-26 | 1
Develop Settings (Admin) Main Page | Programming | Coding | 2015-10-27 | 2015-10-27 | 3
Develop Settings (User) Main Page | Programming | Coding | 2015-10-27 | 2015-10-27 | 3
Develop Import/Export Page | Programming | Coding | 2015-10-26 | 2015-10-27 | 4
Develop Audit Log Page | Programming | Coding | 2015-10-26 | 2015-10-27 | 4
Report Management Module
Integrate "Generate report of volunteers as of today" into Report Page | Programming | Coding | 2016-06-06 | 2016-06-06 | 2 | Marcus, Thao
Integrate "Generate report of members as of specified date" into Report Page | Programming | Coding | 2016-06-07 | 2016-06-07 | 2 | Marcus, Thao
Integrate "Generate report of donations" into Report Page | Programming | Coding | 2016-06-08 | 2016-06-08 | 2 | Marcus, Thao
Integrate "Generate report of events" into Report Page | Programming | Coding | 2016-06-09 | 2016-06-09 | 2 | Marcus, Thao
Preparation for UAT
Integration ▼
Integrating & testing with earlier functionalities | Programming | Integration | 2015-10-29 | 2015-10-30 | 2
Deployment ▼
Deploy application to OpenShift | Programming | Deployment | 2015-10-29 | 2015-10-30 | 2
Regression Testing & Debugging ▼
Testing of application and documenting bugs | Programming | Regression Testing & Debugging | 2015-10-29 | 2015-10-30 | 2
Debugging | Programming | Regression Testing & Debugging | 2015-10-29 | 2015-10-30 | 2
End of Iteration Tasks ▼
Collection Schedule and PP metric | Non-Programming | End of Iteration Task | 2015-10-30 | 2015-10-30 | 1
Code sharing | Non-Programming | End of Iteration Task | 2015-10-30 | 2015-10-30 | 1
End Of Iteration 6 (11/7/16 - 24/7/16)
Start Of Iteration 7 (25/7/16 - 7/8/16)
Iteration Preparation ▼
Preparation/Agenda for Client Meeting (15 June) - Functionalities update - Schedule - Milestone - Buffer Time - Critical Path | Non-Programming | Iteration Preparation | 2016-06-13 | 2016-06-13 | 3 | Darryl
Follow-up after Client Meeting - Update Requirement Change - Mitigation Plan - Update Schedule | Non-Programming | Iteration Preparation | 2016-06-16 | 2016-06-16 | 3 | Darryl
Design ▼
Finish Up documentations | Non-Programming | Design | 2015-11-03 | 2015-11-03 | 2
Final Preparation for UAT test | Non-Programming | Design | 2015-11-02 | 2015-11-06 | 6
Develop test cases (Social Activeness Report) | Non-Programming | Design | 2015-10-26 | 2015-10-26 | 2
Coding ▼
UI Mockup - Reports
Refine UI | Programming | Coding | 2015-10-26 | 2015-10-26 | 1
| Programming | Coding | 2015-10-27 | 2015-10-27 | 3
| Programming | Coding | 2015-10-27 | 2015-10-27 | 3
Final Preparation for UAT/Acceptance
Code Optimization | Programming | Coding | 2016-06-06 | 2016-06-06 | 2 | Marcus, Thao
| Programming | Coding | 2016-06-07 | 2016-06-07 | 2 | Marcus, Thao
Integration ▼
Integrating & testing with earlier functionalities | Programming | Integration | 2015-10-29 | 2015-10-30 | 2
Deployment ▼
Deploy application to OpenShift | Programming | Deployment | 2015-10-29 | 2015-10-30 | 2
Regression Testing & Debugging ▼
Testing of application and documenting bugs | Programming | Regression Testing & Debugging | 2015-10-29 | 2015-10-30 | 2
Debugging | Programming | Regression Testing & Debugging | 2015-10-29 | 2015-10-30 | 2
End of Iteration Tasks ▼
Collection Schedule and PP metric | Non-Programming | End of Iteration Task | 2015-10-30 | 2015-10-30 | 1
Code sharing | Non-Programming | End of Iteration Task | 2015-10-30 | 2015-10-30 | 1
Regression Testing & Debugging ▼
Testing of application and documenting bugs | Programming | Regression Testing & Debugging | 2015-11-02 | 2015-11-04 | 2
Debugging | Programming | Regression Testing & Debugging | 2015-11-04 | 2015-11-07 | 2
Iteration Preparation ▼
Preparation for Acceptance (Schedule) - Timeline representation of schedule - Functionalities update / frameworks / external libraries - Breakdown of work by each member ( Programming & Non- programming) - Problem faced and how we overcame them | Non-Programming | Iteration Preparation | 2015-11-09 | 2015-11-10 | 2
Preparation for Acceptance (Metrics) - Visual Representation of bug and schedule - How we made use of metrics to overcome problems - Example of problem and solution - Challenges faced when collecting metrics | Non-Programming | Iteration Preparation | 2015-11-10 | 2015-11-11 | 2
Preparation for Acceptance (Use of GIT) - How GIT was used - Make use of logs to from PPLog | Non-Programming | Iteration Preparation | 2015-11-11 | 2015-11-12 | 2
Preparation for Acceptance (Others) - Main Takeaways - Conflict Management (if applicable) | Non-Programming | Iteration Preparation | 2015-11-12 | 2015-11-13 | 2
Preparation of slides for the Final Presentation & Rehearsals | Non-Programming | Iteration Preparation | 2015-11-13 | 2015-11-14 | 2
End of Iteration Tasks ▼
Collection Schedule and PP metric | Non-Programming | End of Iteration Task | 2015-11-09 | 2015-11-15 | 1
Code sharing | Non-Programming | End of Iteration Task | 2015-11-09 | 2015-11-15 | 1
End Of Iteration 7 (25/7/16 - 7/8/16)